## Sheet1
WBS | Activities | Duration (days) | Start Date | Start Date
1 | CONCEPT | 84 | 2017-06-14 | 2017-09-06
1.1 | Planning | 19 | 2017-06-14 | 2017-07-03
1.1.1 | Idea Brainstorming | 7 | 2017-06-14 | 2017-06-21
1.1.2 | Identify Problem Domain | 7 | 2017-06-21 | 2017-06-28
1.1.3 | Identify Possible Solutions (Features) | 5 | 2017-06-28 | 2017-07-03
1.2 | Data Gathering | 27 | 2017-07-04 | 2017-07-31
1.2.1 | Survey on Renters | 10 | 2017-07-04 | 2017-07-14
1.2.2 | Survey on Drivers | 10 | 2017-07-12 | 2017-07-22
1.2.3 | Review existing systems | 9 | 2017-07-22 | 2017-07-31
1.3 | Documentation | 36 | 2017-08-01 | 2017-09-06
1.3.1 | Draft of project documentation | 7 | 2017-08-01 | 2017-08-08
1.3.2 | Final Documentation | 29 | 2017-08-08 | 2017-09-06
2 | DESIGN | 105 | 2017-09-22 | 2018-01-05
2.1 | System | 51 | 2017-09-22 | 2017-11-12
2.1.1 | Create SRS | 7 | 2017-09-22 | 2017-09-29
2.1.2 | Design Database | 6 | 2017-09-30 | 2017-10-06
2.1.3 | Create UML Diagrams | 37 | 2017-10-06 | 2017-11-12
2.2 | User Interface | 14 | 2017-12-08 | 2017-12-22
2.2.1 | Create Screen Layouts | 14 | 2017-12-08 | 2017-12-22
2.3 | Review Design | 15 | 2017-12-21 | 2018-01-05
2.3.1 | Finalize the design | 15 | 2017-12-21 | 2018-01-05
3 | DEVELOPMENT
3.1 | Finalize Development Environment
3.2 | Basic User Functionalities
3.2.1 | User Login
3.2.2 | User Registration
3.3 | Renter User Functionalities
3.4 | Driver User Functionalities
4 | IMPLEMENTATION
4.1 | Develop Installation Plan
4.2 | Testing
4.3 | Documentation
4.3.1 | User Manual
5 | MAINTENANCE
5.1 | Software Maintenance
Formulas:
Start Date = [Start Date, row below]