## Carkila Gantt
Task Name | Duration | Start | Finish | Assigned To | % Complete | Status | Comments
-----Planning-----
Meeting | 50d | 2018-01-31 | 2018-04-10 |  | 100%
-----Analysis-----
Analyze Software Requirements | 30d | 2018-01-31 | 2018-03-13
-----Software Development-----
Log-in/Sign-up | 30d
Menu | 30d
Rent Vehicle | 30d
Manage Listing | 30d
Approve Request | 30d
View Profile | 30d
Feedback | 30d
Reports | 30d
-----Documentation-----
Vision | 7d | 2018-01-31 | 2018-02-08
Scope of Work | 7d | 2018-01-31 | 2018-02-08
Work Breakdown Structure | 7d | 2018-01-31 | 2018-02-08
SRS | 7d | 2018-01-31 | 2018-02-08
Others | 10d | 2018-01-31 | 2018-02-13
-----Testing and Assurance-----
Deployment | 15d
Pilot Installation | 15d
User Training | 15d
User Support | 15d
-----Close-Out-----
Finalize Documentation | 10d