## Sheet1
Tasks | Hours | Days | Total Hours
PLANNING
Identify Problem | 4 hours | 5 days | 20
Create Project Plan | 4 hours | 6 days | 24
Update Project Plan | 2 hours | 6 days | 12
Survey | 4 hours | 5 days | 20
Interview | 4 hours | 5 days | 20
Compile Interview + Survey Results | 4 hours | 3 day | 12
Create Project Proposal | 4 hours | 5 days | 20
Status Reports (weekly) | 2 hours | 10 days | 20
Milestones | 2 hours | 6 days | 12
ANALYSIS
Draft of Documentations | 2 hours | 10 days | 20
Create Diagrams | 4 hours | 40 days | 160
Update Diagrams | 4 hours | 20 days | 80
Review Documents + Diagrams | 2 hours | 10 days | 20
Finalize Revisions | 2 hours | 10 days | 20
Create Screen Layouts | 2 hours | 10 days | 20
Review Design | 2 hours | 10 days | 20
DEVELOPMENT
User Interface | 4 hours | 15 days | 60
User Login | 4 hours | 5 days | 20
User Registration | 4 hours | 5 days | 20
Renter User Funtionalities | 4 hours | 15 days | 60
Driver User Functionalities | 4 hours | 15 days | 60
IMPLEMENTATION
Test System | 4 hours | 10 days | 40
Create Test Reports | 4 hours | 5 days | 20
Debug System | 4 hours | 5 days | 20
Implement System | 4 hours | 3 days | 12
PROJECT END
Complete Requirements | 4 hours | 3 days | 12
Finalize Documentations | 4 hours | 3 days | 12
|  | Total= | 836